## Deliverables
FY17 Q1 Deliverable (90 day goal) FIDO Security R & D
Develop a Passwordless UX ( UAF -Universal Authentication Framework ) Major Components: Deliver iOS application and Java Backend Server developed by following FIDO specified UAF protocol. Star feature : Ability to enhance existing username/password logins to Passwordless UX such as Fingerprint input.
Weekly plan
| Description of milestones | Description of updated milestones | Due Date | Status
1 | Develop iOS Client and Java server by following FIDO UAF protocol: Add phone number based one time login for iOS application using SMS OTP Add feature to associate PIN based authenticator for the user Add Database integration for maintaining user registrations and vendor registrations Add feature to perform FIDO Authentication |  | 2016-04-29
2 | Enhance iOS Client and Java server: Add feature to associate Touch ID authenticator for the user Add JAVA REST API to associate a third party vendor with our solution Add feature to perform FIDO Authentication as a response to Push notification from server |  | 2016-05-06
3 | Enhance iOS Client and Java server: Add Java REST API for third party vendor to request for FIDO authentication Add feature to authenticate third party vendor using Push notification Add feature to associate new vendor using iOS client using SMS OTP |  | 2016-05-13
4 | Enhance iOS Client and Java server: Add feature to display UI while associating a third party vendor with our solution Add feature to associate new vendor using iOS client using QR code Add feature to choose authenticator while associating new vendor | Enhance iOS Client and Java server:Link Relying Party website account with PSL FIDO Develop server components for communication between server and relying party Develop relying party website components for communicating with FIDO server Develop iOS client components which create FIDO credentials for relying party account Integrate server and iOS client implementations using Https | 2016-05-20
5 | Enhance iOS Client and Java server: Add feature to perform FIDO authentication while using mobile web browser or other mobile application without push notifications | Enhance iOS Client and Java server: Authenticate Relying Party website account with PSL FIDO Develop server components for communication between server and relying party Develop relying party website components for communicating with FIDO server Develop iOS client components which authenticate FIDO credentials for relying party account Integrate server and iOS client implementations using Https | 2016-05-27
6 | Enhance iOS Client and Java server: Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | Enhance iOS Client and Java server: Analyze FIDO certification requirements and build a report of features required for UAF server, UAF client and UAF Touch ID authenticator Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | 2016-06-03
7 | Enhance iOS Client and Java server: Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | Enhance iOS Client and Java server Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | 2016-06-10
8 | Enhance iOS Client and Java server: Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | Enhance iOS Client and Java server: Test FIDO iOS Client and Java server using FIDO Alliance provided tools for compliance Add /Edit implementation for compliance | 2016-06-17
9 | Enhance iOS Client and Java server: Integrate the complete solution and add features to enhance user experience: Animations/Hints Test solution by integrating with existing websites | Enhance iOS Client and Java server: Integrate the complete solution and add features to enhance user experience: Animations/Hints Test solution by integrating with existing websites | 2016-06-24
| Demonstrate Passwordless UX for a client website | Demonstrate Passwordless UX for a client website | 2016-06-30